## Overview
MeetCopilot — Phase 2 Testing & Verification Checklist
Makes the product sellable and the infrastructure production-live (Milestones 1–7).
How to use | Work top to bottom: create the Accounts, do the Manual Setup, then run the per-milestone Verification steps. Fill the Status column (Pass / Fail / Blocked / N/A) and add Notes. Tackle milestones in order — each builds on the previous.
Components | Monorepo with three apps: apps/desktop (Electron overlay), apps/api (Node/Hono backend, AWS App Runner), apps/web (Next.js on Vercel). Database/auth: Supabase.
What was built | M1 Usage metering · M2 Plan gating + free cap · M3 Deploy API to AWS App Runner · M4 Payments (Razorpay) · M5 Account dashboard (usage meter + billing) · M6 Observability (Sentry/PostHog/Langfuse) · M7 Desktop packaging + Windows code signing.
Sheets | 1) Overview 2) Accounts & Services (sign-ups + keys) 3) Manual Setup (one-time tasks) 4) Verification Checklist (per-milestone tests + expected results).
Key principle | Plan/usage checks and metering are SERVER-SIDE only; subscription status is written ONLY by the idempotent Razorpay webhook; all secrets live in env vars, never committed.
Reference docs | docs/deploy-api-apprunner.md · apps/web/DEPLOYMENT.md · docs/desktop-signing.md · .env.example (root) · apps/web/.env.example
Legend | Required = needed for the core 'stranger can buy and use it' flow. Optional = observability is great to have but each integration no-ops without its keys.

## Accounts & Services
Service | Why it's needed | What to create / get | Env var(s) | Required? | Status
Supabase | Postgres DB, auth, RLS — backbone of users/usage/billing. | Project. Copy Project URL, anon (public) key, service_role key, JWT secret. | SUPABASE_URL, SUPABASE_ANON_KEY, SUPABASE_SERVICE_ROLE_KEY, SUPABASE_JWT_SECRET | Required
AWS | Bedrock LLM inference + host the backend (App Runner) + image registry (ECR). | AWS account. Enable Bedrock model access in us-east-1 (Nova Lite, Claude 3.5 Sonnet). IAM instance role with bedrock:InvokeModelWithResponseStream. | AWS_REGION (+ instance role; or AWS_ACCESS_KEY_ID/SECRET for local) | Required
Deepgram | Default speech-to-text provider. | Console account → API key. | DEEPGRAM_API_KEY | Required
ElevenLabs | Alternative STT provider (optional). | API key (only if testing this provider). | ELEVENLABS_API_KEY | Optional
Sarvam | Alternative STT provider (optional). | API key (only if testing this provider). | SARVAM_API_KEY | Optional
Vercel | Hosts the Next.js web app (marketing, account, webhook). | Project linked to repo, Root Directory = apps/web. Set env vars per apps/web/DEPLOYMENT.md. | (all NEXT_PUBLIC_* + server secrets in Vercel) | Required
Razorpay | Payments / subscriptions (M4). | Account (start in Test Mode). API key id + secret. Create a Plan for the paid tier. Add a Webhook → /api/razorpay/webhook (subscription.* events) with a secret. | RAZORPAY_KEY_ID, RAZORPAY_KEY_SECRET, RAZORPAY_WEBHOOK_SECRET, RAZORPAY_PLAN_ID | Required
Google Cloud | Google sign-in option in Supabase Auth (used by /login). | OAuth client configured in Supabase Auth providers (may already be set up). | (configured in Supabase dashboard) | Optional
Sentry | Crash/error reporting across all 3 apps (M6). | 3 projects (api, desktop, web). Copy each DSN. | SENTRY_DSN_API, SENTRY_DSN_DESKTOP, SENTRY_DSN_WEB (+ NEXT_PUBLIC_SENTRY_DSN_WEB) | Optional
PostHog | Product analytics events (M6). | Project → Project API key + host. | POSTHOG_KEY, POSTHOG_HOST (+ NEXT_PUBLIC_ copies for web client) | Optional
Langfuse | Per-LLM-call cost + latency tracing (M6). | Project → public + secret keys. | LANGFUSE_PUBLIC_KEY, LANGFUSE_SECRET_KEY, LANGFUSE_BASEURL | Optional
Code signing | Sign the Windows installer so there is no 'Unknown Publisher' warning (M7). Pick ONE. | Azure Trusted Signing account, OR SSL.com eSigner subscription, OR a local OV/EV .pfx certificate. | SIGN_PROVIDER + provider creds (see docs/desktop-signing.md) | Required (M7)

## Manual Setup
# | Task | Where | Details | Done?
1 | Apply migration 0002_usage_metering.sql | Supabase SQL editor | Adds usage_sessions.stt_seconds, usage_events.cost_usd, end_usage_session RPC. Additive only.
2 | Apply migration 0003_usage_limits.sql | Supabase SQL editor | Adds get_user_usage RPC used for server-side cap enforcement.
3 | Apply migration 0004_billing_webhooks.sql | Supabase SQL editor | Adds webhook_events table, subscriptions.last_event_at, process_subscription_event RPC (idempotent).
4 | Fill root .env from .env.example | Local machine | Supabase URL/keys/JWT secret/service role, Deepgram, AWS, optional caps + observability keys.
5 | Enable Bedrock model access | AWS Bedrock console (us-east-1) | Request access to Amazon Nova Lite and Anthropic Claude 3.5 Sonnet before first inference.
6 | Build + push API image, create App Runner service | AWS (ECR + App Runner) | Follow docs/deploy-api-apprunner.md: port 8787, health check /health, instance role with Bedrock perms, env vars.
7 | Point clients at the deployed API | Desktop env + Vercel | Set API_URL (desktop build) and NEXT_PUBLIC_API_BASE_URL (Vercel) to the App Runner URL.
8 | Set Vercel environment variables | Vercel dashboard | NEXT_PUBLIC_SUPABASE_*, SUPABASE_SERVICE_ROLE_KEY, RAZORPAY_* and observability — see apps/web/DEPLOYMENT.md.
9 | Set Supabase Auth redirect URLs | Supabase dashboard | Add https://<domain>/auth/callback (and Vercel domain). Do NOT add meetcopilot://.
10 | Create Razorpay Plan + Webhook | Razorpay dashboard | Plan id -> RAZORPAY_PLAN_ID. Webhook -> /api/razorpay/webhook, subscription.* events, secret -> RAZORPAY_WEBHOOK_SECRET.
11 | Create observability projects + keys | Sentry / PostHog / Langfuse | Set keys in root .env (api + desktop) and Vercel (web). Each integration no-ops if unset.
12 | Choose + set up code signing | Local / CI build machine | Install the tool (trusted-signing-cli / SSL.com CodeSignTool / Windows SDK signtool); set SIGN_PROVIDER + creds. See docs/desktop-signing.md.
13 | Set electron-builder cache env then package | Local Windows | $env:ELECTRON_BUILDER_CACHE='D:\eb-cache'; $env:TEMP='D:\eb-tmp'; $env:TMP='D:\eb-tmp'; then pnpm --filter @meetcopilot/desktop package.

## Verification Checklist
# | What to verify | Action (how to test) | Expected result | Status | Notes
M1 — Usage metering (apps/api)
1 | Session row is written | Sign in on desktop, Start capture, speak so You/Them transcribe, Stop. | usage_sessions has one new row with started_at, ended_at set, and stt_seconds ~= how long you captured.
2 | Inference events are written | During capture press Ctrl+Enter once or twice to get an answer. | usage_events has one 'infer' row per ask with model, tokens_in, tokens_out, and cost_usd > 0.
3 | STT seconds are server-computed | Compare stt_seconds to the wall-clock capture duration. | They match within a few seconds (derived from ended_at - started_at, not client-reported).
M2 — Plan gating + free cap (server-side)
1 | Free cap blocks a new session | Set FREE_MAX_SESSIONS=1 in API env, restart. As a free user run 1 session, Stop, then Start capture again. | Second start is blocked: red upgrade banner appears, capture tears down, STT status shows 'limit reached'.
2 | Upgrade prompt links to pricing | Click 'Upgrade' on the banner. | System browser opens the web pricing page (WEB_URL/#pricing).
3 | 80% soft warning | Set FREE_MAX_SESSIONS=2, reset usage (delete user's usage_sessions). Run one session, then Start again. | An amber 'approaching the free limit (1/2 sessions...)' banner shows, but capture still proceeds.
4 | /infer is gated | While over the cap, press Ctrl+Enter. | No answer streams; the limit banner shows instead (HTTP 402 from /infer).
5 | /stt-token is gated server-side | Over the cap, observe the STT token request (or call POST /stt-token with the user's token). | Returns 402 limit_reached — the client cannot bypass the cap.
M3 — Deploy API to AWS App Runner
1 | Image builds | From repo root: docker build -f apps/api/Dockerfile -t meetcopilot-api . | Build completes with no errors and produces the image.
2 | Local container healthy (optional) | docker run --rm -p 8787:8787 --env-file .env meetcopilot-api ; curl http://127.0.0.1:8787/health | Returns {"ok":true,"service":"MeetCopilot backend",...}.
3 | App Runner service is live | Push to ECR, create the App Runner service (port 8787, health /health, instance role, env vars). curl the URL/health. | Service reaches Running; /health returns ok over HTTPS.
4 | Desktop works against deployed API | Set API_URL to the App Runner URL, launch desktop, sign in, capture + ask. | Answers stream from the deployed backend; usage rows appear in Supabase.
5 | Web points at the API | Set NEXT_PUBLIC_API_BASE_URL in Vercel, redeploy. | Value is present in the deployed web env (used by the M5 usage meter).
M4 — Payments via Razorpay
1 | Checkout creates a subscription | On /account as a free user click 'Upgrade to Pro' and pay with a Razorpay test card. | Razorpay Checkout completes; no error. (subscriptions is NOT written by checkout itself.)
2 | Webhook unlocks the plan | Let the subscription.activated/charged webhook fire. | subscriptions row shows status=active, plan=pro, provider=razorpay, current_period_end set.
3 | Plan reflected to the user | Refresh /account; check the desktop free cap. | Account shows Pro plan; desktop free cap is lifted (unlimited).
4 | Replay = no double-write (idempotency) | In Razorpay, re-deliver the SAME webhook event. | Handler responds applied:false; subscriptions row unchanged (updated_at not bumped); only one webhook_events row for that id.
5 | Out-of-order safety | Re-deliver an older event after a newer one (if available). | The stale event does not overwrite the newer subscription state.
M5 — Account dashboard (apps/web /account)
1 | Usage meter (free user) | Set NEXT_PUBLIC_API_BASE_URL, sign in as a free user, open /account. | Usage card shows sessions x/cap and minutes x/cap with progress bars (amber >=80%, red at cap).
2 | Upgrade CTA for free users | Look at the plan + billing cards. | Plan shows Free; an 'Upgrade to Pro' button and a Free billing note are shown.
3 | Paid plan details | As a subscribed user, open /account. | Plan shows Pro, 'Renews on <date>' appears, and the meter shows 'Unlimited'.
4 | Manage billing opens portal | Click 'Manage billing'. | A new tab opens the Razorpay-hosted subscription page for the user.
5 | Graceful degrade | Unset NEXT_PUBLIC_API_BASE_URL (or stop the API) and reload /account. | Usage card shows 'Usage will appear here once the backend is reachable' (no crash).
M6 — Observability (all 3 apps)
1 | Sentry receives errors | Set the SENTRY_DSN_* vars. Trigger an error (e.g. misconfigure Bedrock and call /infer, or force a renderer error). | An issue appears in the matching Sentry project (api / desktop / web).
2 | PostHog product events | With POSTHOG keys set: sign in (web), click Download, run first desktop session + ask, hit the cap, subscribe. | Events signed_in, download, first_session, first_answer, hit_cap, upgrade appear in PostHog Activity.
3 | Langfuse LLM traces | With Langfuse keys set, make an /infer call. | A trace with one generation shows model, input/output tokens, estimated cost, and latency.
4 | No-op without keys | Leave all observability vars unset and run the apps. | Everything works normally; nothing is sent (no errors from telemetry).
M7 — Desktop packaging + Windows code signing
1 | Unsigned dev build still works | Leave SIGN_PROVIDER unset; set the cache env; run pnpm --filter @meetcopilot/desktop package. | release/MeetCopilot Setup <ver>.exe is produced (unsigned), no signing error.
2 | Signed build is produced | Set SIGN_PROVIDER + provider creds (see docs/desktop-signing.md); package again. | Packaging runs the sign hook for each PE file; the installer is produced.
3 | Signature is valid | PowerShell: Get-AuthenticodeSignature '.\apps\desktop\release\MeetCopilot Setup <ver>.exe' ¦ Format-List | Status: Valid, and SignerCertificate shows your publisher.
4 | No 'Unknown Publisher' on install | Run the installer on a clean Windows machine. | UAC/SmartScreen shows your verified publisher name; no 'Unknown Publisher' warning.